## Slide 1: UBER Case Study – Project plan
Subhrapratim Bairagi

## Slide 2: Project Charter
Scope of Project plan
  Integration plan of new workflow with In-house Labelling tool.
  Delivery of 20,000 labelling tasks by October 2020.
Assumption
  Task labelling activities of data from Multi-sensor configuration, currently in Production. Considering Start date of 24th August 2020.
  1:1 mapping between a task and the data to be labelled. For example, there'd be 1 task for each image, video, or LiDAR sequence needing to be labelled.
  With increase in no. of users, In-house labelling tool is scalable and reliable in terms of IT infrastructure.
  No major development challenge in integrating new workflow with existing tool. Since manual orchestration of parallel workflow is successful and minimal change in UI & Backend required.
  Activities Task A, Task B & QA both in sequential and parallel scenarios.
  Team of 2 operators for Sequential activities & Team of 3 operators for Parallel activities.

## Slide 3: Work Breakdown Structure
Project – Scaling New workflow
Data processing
Data labelling operations
Product
Tool development
Pre-processing
Data formats
Batching into datasets
Post-processing
Labelled datasets for label consumers
Labelling
LiDAR data
Camera Image
Map data
QA
Integrate New workflow
UI
Backend
QA
Training resource
Additional object types – multi sensors configuration
Labelling instructions

## Slide 4: Project timeline
Labelled data delivered to Production support across 10 batches over 47 days with an end date of 28th Oct’20

## Slide 5: Scenario Analysis
Chart: Considering scenario: Scaling to new workflow after 2 weeks
Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47
No. of Tasks completed | 307.6923 | 307.6923 | 307.6923 | 307.6923 | 307.6923 | 307.6923 | 307.6923 | 307.6923 | 307.6923 | 307.6923 | 460.6172 | 460.6172 | 460.6172 | 460.6172 | 460.6172 | 460.6172 | 460.6172 | 460.6172 | 460.6172 | 460.6172 | 460.6172 | 460.6172 | 460.6172 | 460.6172 | 460.6172 | 460.6172 | 460.6172 | 460.6172 | 460.6172 | 460.6172 | 460.6172 | 460.6172 | 460.6172 | 460.6172 | 460.6172 | 460.6172 | 460.6172 | 460.6172 | 460.6172 | 460.6172 | 460.6172 | 460.6172 | 460.6172 | 460.6172 | 460.6172 | 460.6172 | 460.6172
Cumulative No. of Task labelled | 307.6923 | 615.3846 | 923.0769 | 1230.7692 | 1538.4615 | 1846.1538 | 2153.8462 | 2461.5385 | 2769.2308 | 3076.9231 | 3537.5403 | 3998.1575 | 4458.7748 | 4919.392 | 5380.0092 | 5840.6264 | 6301.2437 | 6761.8609 | 7222.4781 | 7683.0953 | 8143.7126 | 8604.3298 | 9064.947 | 9525.5643 | 9986.1815 | 10446.7987 | 10907.4159 | 11368.0332 | 11828.6504 | 12289.2676 | 12749.8848 | 13210.5021 | 13671.1193 | 14131.7365 | 14592.3538 | 15052.971 | 15513.5882 | 15974.2054 | 16434.8227 | 16895.4399 | 17356.0571 | 17816.6743 | 18277.2916 | 18737.9088 | 19198.526 | 19659.1433 | 20119.7605
Sl. No | Workflow scaling after no. of weeks | Days require to complete 20K labelling tasks | End date
1 | 1 | 45 | 24th Oct’20
2 | 2 | 47 | 28th Oct’20
3 | 3 | 48 | 29th Oct’20
4 | 4 | 50 | 2nd Nov’20
5 | 5 | 52 | 4th Nov’20
Impact on No. of days to complete labelling task
by introducing workflow scaling at different timelines
Recommended
Not feasible
If workflow scaling fails it will remain a sequential process and will require 65 days to deliver labelled data with an end date of 20th Nov’20

## Slide 6: Risk Assessment
Identified risks | Potential response | Root cause | Owner
If scale to new workflow fails then it will delay the delivery plan of October’20 | Availability of On demand additional operators which will incur additional cost | Product/ Engineering challenges | Engineering Manager
If new scaling workflow becomes less productive in terms of UI/ non automated cognitive load this might slowdown the overall labelling process | Product team to research and test workflow use cases to automate error prone manual handover | Non-scalable IT infrastructure poses risk with growing data variety & object types | Product Team
If new object types for labelling from variety of sensor data not well defined then effectiveness of sensor fusion data will be reduced | Domain experts/ Product team should provide detailed instructions about object types with examples | Increase in multi sensor configuration without detailed instruction can lead to reduced effectiveness | Domain experts
Attrition of qualified operators can impact delivery schedules | Ramp up new operators with Process tutorials | Unclear SLAs with Vendor on Quality and Delivery metrics | Program Manager
Fail to comply with data privacy regulations & ethical use of data can lead to compliance issues and can cost the organization | Masking data during pre-processing. | Not keeping track of local regulatory laws can led to compliance issues | Program Manager

## Slide 7: Recommendation
To achieve delivery of 20,000 tasks by October 2020 its recommended to employ both sequential and parallel processes.
Option 1: Integration of scaled workflow from 2nd week onwards will complete 20,000 labelling tasks in 45 days
Option 2: Integration of scaled workflow from 3rd week onwards will complete 20,000 labelling tasks in 47 days
Option 3: Integration of scaled workflow from 4th week onwards will complete 20,000 labelling tasks in 48 days
Hence, its feasible to plan for Option 2 in order to optimize delivery timelines without incurring additional cost.
However, if scale to new workflow fails, it’ll require 65 days to complete tasks. Hence, project will incur cost in terms of additional operators to deliver task by On time.

## Slide 8: Appendix
Case information |  |  | 
Sl. no. | Particular | Figure | Units
1 | Total no. of Tasks planned | 20000 | tasks
2 | Previous single sensor configuration - Time required for task labelling | 12 | hrs
3 | Multi-sensor configuration - Status quo workflow - Time required for task labelling | 26 | hrs
4 | Multi-sensor configuration - Parallel workflow - Efficiency gain | 34% | 
5 | Multi-sensor configuration - Parallel workflow - Time required for task labelling | 17.16 | hrs
6 | Quality target for labelling tasks | 95% | 
7 | No. of operators | 1000 | nos.
8 | Per day effort capacity (assuming) | 8 | hrs
9 | QA effort in % of task labelling effort (assuming) | 20% | 
10 | No. of days in work week | 5 | days
11 | Total no. of days remaining for October 2020 delivery target (24th August'20 to 31st October'20) | 50 | days
Sequential Workflow |  |  | 
Assuming 1 labeller & 1 QA work on each task |  |  | 
Sl. no | Particular | Figure | Units
1 | No. of operator | 2 | nos.
2 | Each task duration | 26 | hrs
3 | Task A (calculated) | 10.4 | hrs
4 | Task B (precedence Task A) | 10.4 | hrs
5 | QA | 5.2 | hrs
6 | Hence total task labelling duration | 26 | hrs
7 | No. of labelled task completed by Team of 2 operators in 1 week | 3.076923 | tasks
8 | No. of task labelled by 1000 operator (Team of 2) in 1 week | 1538 | tasks
9 | To complete 20K tasks it will require | 65 | days
New Parallel Workflow |  |  | 
Assuming 2 labeller & 1 QA work on each task |  |  | 
Sl. no | Particular | Figure | Units
1 | No. of operator | 3 | nos.
2 | Each task duration | 17.16 | hrs
3 | Task A (calculated) | 10.4 | hrs
4 | Task B (parallel to Task A lead to 34% efficiency gain) | 13.936 | hrs
5 | QA | 5.2 | hrs
6 | Hence total task labelling duration | 17.368 | hrs
7 | No. of labelled task completed by Team of 3 operators in 1 week | 6.909258 | tasks
8 | No. of task labelled by 1000 operator (Team of 3) in 1 week | 2303 | tasks
9 | To complete 20K tasks it will require | 43 | days