## Workflow analysis
Project Plan Effort Assessment
Case information
Sl. no. | Particular | Figure | Units | Sequential Workflow |  |  |  | New Parallel Workflow |  |  |  | Scenario analysis |  |  | Considering scenario: Scaling to new workflow after 2 weeks
1 | Total no. of Tasks planned | 20000 | tasks | Assuming 1 labeller & 1 QA work on each task |  |  |  | Assuming 2 labeller & 1 QA work on each task
2 | Previous single sensor configuration - Time required for task labelling | 12 | hrs | Sl. no | Particular | Figure | Units | Sl. no | Particular | Figure | Units | Sl. No | Scaling after no. of weeks | Days require to complete 20K labelling tasks | Day | No. of Tasks completed | Cumulative No. of Task labelled
3 | Multi-sensor configuration - Status quo workflow - Time required for task labelling | 26 | hrs | 1 | No. of operator | 2 | nos. | 1 | No. of operator | 3 | nos. | 1 | 1 | 45.08 | 1 | 307.6923 | 307.6923
4 | Multi-sensor configuration - Parallel workflow - Efficiency gain | 34% |  | 2 | Each task duration | 26 | hrs | 2 | Each task duration | 17.16 | hrs | 2 | 2 | 46.74 | 2 | 307.6923 | 615.3846
5 | Multi-sensor configuration - Parallel workflow - Time required for task labelling | 17.16 | hrs | 3 | Task A (calculated) | 10.4 | hrs | 3 | Task A (calculated) | 10.4 | hrs | 3 | 3 | 48.4 | 3 | 307.6923 | 923.0769
6 | Quality target for labelling tasks | 95% |  | 4 | Task B (precedence Task A) | 10.4 | hrs | 4 | Task B (parallel to Task A lead to 34% efficiency gain) | 13.936 | hrs | 4 | 4 | 50.06 | 4 | 307.6923 | 1230.7692
7 | No. of operators | 1000 | nos. | 5 | QA | 5.2 | hrs | 5 | QA | 5.2 | hrs | 5 | 5 | 51.72 | 5 | 307.6923 | 1538.4615
8 | Per day effort capacity (assuming) | 8 | hrs | 6 | Hence total task labelling duration | 26 | hrs | 6 | Hence total task labelling duration | 17.368 | hrs |  |  |  | 6 | 307.6923 | 1846.1538
9 | QA effort in % of task labelling effort (assuming) | 20% |  | 7 | No. of labelled task completed by Team of 2 operators in 1 week | 3.0769 | tasks | 7 | No. of labelled task completed by Team of 3 operators in 1 week | 6.9093 | tasks |  |  |  | 7 | 307.6923 | 2153.8462
10 | No. of days in work week | 5 | days | 8 | No. of task labelled by 1000 operator (Team of 2) in 1 week | 1538.4615 | tasks | 8 | No. of task labelled by 1000 operator (Team of 3) in 1 week | 2303.0861 | tasks |  |  |  | 8 | 307.6923 | 2461.5385
11 | Total no. of days remaining for October 2020 delivery target (24th August'20 to 31st October'20) | 50 | days | 9 | To complete 20K tasks it will require | 65 | days | 9 | To complete 20K tasks it will require | 43.42 | days |  |  |  | 9 | 307.6923 | 2769.2308
[15 empty] | 10 | 307.6923 | 3076.9231
[15 empty] | 11 | 460.6172 | 3537.5403
[15 empty] | 12 | 460.6172 | 3998.1575
[15 empty] | 13 | 460.6172 | 4458.7748
[15 empty] | 14 | 460.6172 | 4919.392
[15 empty] | 15 | 460.6172 | 5380.0092
[15 empty] | 16 | 460.6172 | 5840.6264
[15 empty] | 17 | 460.6172 | 6301.2437
[15 empty] | 18 | 460.6172 | 6761.8609
[15 empty] | 19 | 460.6172 | 7222.4781
[15 empty] | 20 | 460.6172 | 7683.0953
[15 empty] | 21 | 460.6172 | 8143.7126
[15 empty] | 22 | 460.6172 | 8604.3298
[15 empty] | 23 | 460.6172 | 9064.947
[15 empty] | 24 | 460.6172 | 9525.5643
[15 empty] | 25 | 460.6172 | 9986.1815
[15 empty] | 26 | 460.6172 | 10446.7987
[15 empty] | 27 | 460.6172 | 10907.4159
[15 empty] | 28 | 460.6172 | 11368.0332
[15 empty] | 29 | 460.6172 | 11828.6504
[15 empty] | 30 | 460.6172 | 12289.2676
[15 empty] | 31 | 460.6172 | 12749.8848
[15 empty] | 32 | 460.6172 | 13210.5021
[15 empty] | 33 | 460.6172 | 13671.1193
[15 empty] | 34 | 460.6172 | 14131.7365
[15 empty] | 35 | 460.6172 | 14592.3538
[15 empty] | 36 | 460.6172 | 15052.971
[15 empty] | 37 | 460.6172 | 15513.5882
[15 empty] | 38 | 460.6172 | 15974.2054
[15 empty] | 39 | 460.6172 | 16434.8227
[15 empty] | 40 | 460.6172 | 16895.4399
[15 empty] | 41 | 460.6172 | 17356.0571
[15 empty] | 42 | 460.6172 | 17816.6743
[15 empty] | 43 | 460.6172 | 18277.2916
[15 empty] | 44 | 460.6172 | 18737.9088
[15 empty] | 45 | 460.6172 | 19198.526
[15 empty] | 46 | 460.6172 | 19659.1433
[15 empty] | 47 | 460.6172 | 20119.7605